## Change Register
Title | Summary | Risk | ScheduledStart | Site | Owner | Status
CHG-1042 | Core router OS upgrade - Sydney POP | High | 2026-10-21 | Sydney POP | Network Engineering Lead | Pending Approval
CHG-1043 | Firewall rule base clean-up - Melbourne DC | Medium | 2026-10-19 | Melbourne DC | Security Operations | Approved
CHG-1044 | DWDM line card replacement - Brisbane POP | High | 2026-10-22 | Brisbane POP | Transport Engineer | Approved
CHG-1045 | Edge switch firmware patch - Perth POP | Low | 2026-10-20 | Perth POP | Field Technician | Scheduled
CHG-1046 | BGP peering migration to new IX port - Sydney IX | High | 2026-10-23 | Sydney IX | Peering Manager | Pending Approval
CHG-1047 | NTP server replacement - Adelaide DC | Low | 2026-10-20 | Adelaide DC | Systems Engineer | Scheduled
CHG-1048 | Monitoring agent rollout - all POPs | Medium | 2026-10-24 | All POPs | NOC Manager | Approved
CHG-1049 | UPS battery replacement - Canberra POP | Medium | 2026-10-25 | Canberra POP | Facilities Engineer | Scheduled