# Method Statement - CHG-1042

Core router OS upgrade - Sydney POP - Network Operations

| Field | Value |
| --- | --- |
| Change ID | CHG-1042 |
| Site | Sydney POP |
| Risk | High |
| Window | 2026-10-21 00:00-04:00 AEDT |
| Owner | Network Engineering Lead |
| Status | Pending Approval |

# 1. Scope

Upgrade the operating system on core routers SYD-CR-01 and SYD-CR-02 from release 7.4 to 7.9 to address vendor security advisories. Routers are upgraded one at a time; traffic is drained to the peer router before each upgrade.

# 2. Pre-checks

Confirm a current configuration backup for both routers.

Stage the configuration diff between 7.4 and 7.9 and have it peer reviewed.

Run the pre-change validation script and confirm zero errors.

Record BGP neighbour states, route counts and interface status as a baseline.

Confirm the NOC is staffed and the vendor support case is open.

# 3. Implementation Steps

| Step | Action | Owner | Expected Result | Duration |
| --- | --- | --- | --- | --- |
| 1 | Announce start of window to NOC bridge | Change Manager | NOC acknowledged | 5 min |
| 2 | Drain traffic from SYD-CR-01 (raise IGP metric) | Network Engineer | Traffic on SYD-CR-02 | 15 min |
| 3 | Install OS 7.9 on SYD-CR-01 and reload | Network Engineer | Router boots on 7.9 | 30 min |
| 4 | Verify BGP sessions and route counts vs baseline | Network Engineer | All sessions Established | 15 min |
| 5 | Restore traffic to SYD-CR-01 | Network Engineer | Traffic balanced | 10 min |
| 6 | Repeat steps 2-5 for SYD-CR-02 | Network Engineer | Both routers on 7.9 | 70 min |
| 7 | Post-change monitoring and close-out | NOC Manager | No alarms for 30 min | 30 min |

# 4. Rollback Plan

If any BGP session fails to re-establish within 10 minutes, or route counts differ from the baseline by more than 2%, keep traffic drained, boot the router from the retained 7.4 image, restore the backed-up configuration and verify against the baseline. Rollback time per router is approximately 30 minutes.

# 5. Communications Plan

| When | Audience | Channel | Message |
| --- | --- | --- | --- |
| T-48h | Service desk, key accounts | Email | Planned maintenance notice |
| T-0 | NOC, change team | Bridge call | Window start |
| Each step | NOC | Bridge call | Step status |
| T+end | Service desk, CAB | Email | Completion or rollback summary |

# 6. Risk Assessment

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Configuration mismatch after upgrade breaks BGP | Medium | High | Staged config diff and pre-change validation script |
| Router fails to boot new image | Low | High | Retained 7.4 image; vendor on standby |
| Loss of redundancy during upgrade | Medium | Medium | One router at a time; low-traffic window |